## Sheet1
| 2015-02-10 | 2015-02-13 | 2015-02-17 | 2015-02-20 | 2015-02-24 | 2015-02-27 | 2015-03-03 | 2015-03-06 | 2015-03-10 | 2015-03-13 | 2015-03-17 | 2015-03-20 | 2015-03-24 | 2015-03-27 | 2015-03-31 | 2015-04-03 | 2015-04-07 | 2015-04-10 | 2015-04-14 | 2015-04-17 | 2015-04-21 | 2015-04-24 | 2015-04-27 | 2015-05-01
Electronics
Purchase Materials | bar: 2015-02-10 to 2015-02-13
Test Electronics | bar: 2015-02-10 to 2015-02-17
Test Motor | bar: 2015-02-10 to 2015-02-20
Component Layout | bar: 2015-02-10 to 2015-02-27
Construct Control Box | bar: 2015-02-24 to 2015-03-06
Test Control Box | bar: 2015-02-27 to 2015-03-10
Construct Control Panel | bar: 2015-03-03 to 2015-03-24
Test Control Panel | bar: 2015-03-10 to 2015-03-27
Wire Routing | bar: 2015-03-10 to 2015-03-13; 2015-03-24 to 2015-04-07
Full Electronics Test | bar: 2015-03-10 to 2015-03-13; 2015-03-27 to 2015-04-07
Structural
Purchase Tubing Materials | bar: 2015-02-10 to 2015-02-13
Purchase Shell, Fasteners, Misc
Cut/Prep Frame Members | bar: 2015-02-10 to 2015-02-20
Weld Frame Members | bar: 2015-02-10 to 2015-02-27
Machine Motor Mount | bar: 2015-02-27 to 2015-03-13
Drill and Machine Shell | bar: 2015-03-03 to 2015-03-10
Attach Shell | bar: 2015-03-06 to 2015-03-13
Paint Structure | bar: 2015-03-13 to 2015-03-20
Headstock
Design Headstock | bar: 2015-02-10 to 2015-02-20
Purchase Materials | bar: 2015-02-17 to 2015-02-20
????????
????????
????????
Fixturing
machine dovetails | bar: 2015-03-03 to 2015-03-27
machine gibs
machine acme nuts
machine end plates
machine swivel parts
fit dovetails
machine vise jaws
make jaw extensions
assembly
fitting and scraping | bar: 2015-04-24 to 2015-04-27